## Citrix Cloud POC Scorecard
Category | Criteria | Target / KPI | Measurement Method | Status
Architecture | Cloud Connectors in AWS operational | ≥ 2 connectors per region, HA validated | Connectivity & failover testing
Architecture | Hybrid connectivity | On-prem + Citrix Cloud coexistence works | Launch apps from both environments
User Experience | Login time | < 30 sec (target vs on-prem baseline) | Director/Analytics session logs
User Experience | ICA/HDX latency | < 100 ms ICA RTT | Director/HDX Insight
User Experience | Profile handling | FSLogix/UPM works consistently | UAT, logon/logoff tests
User Experience | Banking app performance | Same or better than on-prem | UAT with pilot users
Security | Authentication | MFA/Conditional Access enforced | Test logons + security logs
Security | Data encryption | TLS 1.2+ in transit, KMS at rest validated | Network trace, AWS KMS audit
Security | Compliance | PCI DSS / SOC 2 / ISO alignment confirmed | Citrix + internal security review
Security | Audit logging | All admin/user actions logged & exported | SIEM integration test
Performance | Autoscaling VDAs in AWS | Scale-out/in tested, cost optimized | Autoscale config + AWS billing check
Performance | Resource usage | VDAs stable under load (CPU < 80%) | Load testing, CloudWatch, Director
Operations | Monitoring & visibility | Director + Analytics dashboards in use | Review dashboards, alerts in Splunk/SIEM
Operations | DR/HA | Failover tested (multi-AZ/region if req.) | Simulated connector/region outage
Cost | Citrix Cloud licensing | Model understood, mapped to user base | Licensing workshop + usage reporting
Cost | AWS resource cost | Cost estimation validated vs budget | AWS Cost Explorer + POC billing
Cost | Cost optimization | Power mgmt. policies save ≥ X% | Test scheduled VDA shutdown/startup
Business Outcome | End-user acceptance | ≥ 90% satisfaction from pilot users | Feedback survey
Business Outcome | Governance approval | Security/Compliance teams sign-off | Formal approval meeting
Business Outcome | Go/No-Go decision | Consensus from IT + Business stakeholders | Steering committee